## Dashboard
Home Renovation — Project Dashboard
Everything here updates from the Tasks sheet. Yellow cells are yours to fill in.
Possession date | 2026-11-04 |  | Overdue items | 0
Today | 2026-10-20 |  | Due in next 7 days | 0
Days until possession | 15 |  | Overall progress | 0%
Area | Tasks | Sub-tasks | In Progress | Done | % Complete | Next Due | Budget ($) | Est. Cost ($) | Actual ($) | Remaining Budget ($) | Variance vs Est. ($)
Admin & Possession | 2 | 6 | 0 | 0 | 0% | 2026-11-04 |  | 0 | 0 |  | 0
Mold Remediation | 4 | 10 | 0 | 0 | 0% | 2026-11-06 |  | 0 | 0 |  | 0
Electrical Rough-in | 3 | 6 | 0 | 0 | 0% | 2026-11-10 |  | 0 | 0 |  | 0
Networking | 1 | 6 | 0 | 0 | 0% | 2026-11-10 |  | 0 | 0 |  | 0
Security Cameras | 1 | 4 | 0 | 0 | 0% | 2026-11-10 |  | 0 | 0 |  | 0
Insulation | 2 | 4 | 0 | 0 | 0% | 2026-11-13 |  | 0 | 0 |  | 0
Lighting & Pot Lights | 3 | 3 | 0 | 0 | 0% | 2026-11-13 |  | 0 | 0 |  | 0
Kitchen | 10 | 3 | 0 | 0 | 0% |  |  | 0 | 0 |  | 0
Laundry Room | 7 | 0 | 0 | 0 | 0% |  |  | 0 | 0 |  | 0
Upstairs Bath 1 | 8 | 0 | 0 | 0 | 0% |  |  | 0 | 0 |  | 0
Upstairs Bath 2 | 8 | 0 | 0 | 0 | 0% |  |  | 0 | 0 |  | 0
Trim & Doors (Whole House) | 6 | 0 | 0 | 0 | 0% |  |  | 0 | 0 |  | 0
Other | 0 | 0 | 0 | 0 | 0% |  |  | 0 | 0 |  | 0
TOTAL | 55 | 42 | 0 | 0 | 0% | 2026-11-04 | 0 | 0 | 0 | 0 | 0
Recommended order of work
1. Mold assessment → remediation → clearance test (fix the moisture source, not just the mold).
2. While the attic is open: all ceiling wiring — pot lights, bath fans, Cat6 drops, Wi-Fi APs, camera PoE runs — then electrical rough-in inspection.
3. Insulation goes in only after wiring is done and inspected (attic first, then basement walls).
4. Rough-in plumbing/electrical for kitchen, laundry & baths → drywall → tile, cabinets, flooring.
5. Paint, then trim & doors last so they aren't damaged by other trades.
6. Light fixtures, pot light trims, switches, cameras and network gear go in at the very end.
Formulas:
Next Due = IFERROR(IF(MINIFS(Tasks!$J5:J500,Tasks!$C5:C500,[Area],Tasks!$E5:E500,"<>Done")=0,"",MINIFS(Tasks!$J5:J500,Tasks!$C5:C500,[Area],Tasks!$E5:E500,"<>Done")),"")
Next Due = IFERROR(IF(MIN(G9:[Next Due, row above])=0,"",MIN(G9:[Next Due, row above])),"")

## Tasks
Renovation Task Tracker
How to use: fill the white columns (A–O, T). Grey columns (P–S) calculate automatically. For a sub-task, give it its own ID (e.g. KIT-2.4) and put the parent's ID (KIT-2) in Parent ID. Enter costs on sub-tasks (or on tasks with no sub-tasks) so totals aren't double-counted. Dates are targets — adjust as quotes come in.
ID | Parent ID | Area | Task / Sub-task | Status | Priority | Phase | Assigned To | Start | Due | Done Date | Depends On | Permit / Inspection? | Est. Cost ($) | Actual Cost ($) | Variance ($) | # Sub-tasks | Progress | Flag | Notes
ADM-1 |  | Admin & Possession | Take possession of home | Planned | High | 1 - Remediation | DIY | 2026-11-04 | 2026-11-04 |  |  | No |  |  |  | 4 | 0% |  | Key day: Wed Nov 4, 2026
ADM-1.1 | ADM-1 | Admin & Possession | Change locks / reprogram garage openers | Not Started | High | 1 - Remediation | DIY | 2026-11-04 | 2026-11-05 |  |  | No |  |  |  | 0 | 0%
ADM-1.2 | ADM-1 | Admin & Possession | Transfer utilities & confirm home insurance start date | Not Started | High | 1 - Remediation | DIY | 2026-11-04 | 2026-11-04 |  |  | No |  |  |  | 0 | 0% |  | Hydro, gas, water, internet
ADM-1.3 | ADM-1 | Admin & Possession | Photo/video document existing condition of every room | Not Started | Medium | 1 - Remediation | DIY | 2026-11-04 | 2026-11-05 |  |  | No |  |  |  | 0 | 0% |  | Useful for insurance and before/after
ADM-1.4 | ADM-1 | Admin & Possession | Locate & label electrical panel; note amperage & free breaker slots | Not Started | High | 1 - Remediation | DIY | 2026-11-04 | 2026-11-06 |  |  | No |  |  |  | 0 | 0% |  | Needed before planning pot lights & new circuits
ADM-2 |  | Admin & Possession | Permits & approvals | Not Started | High | 1 - Remediation | DIY | 2026-11-04 | 2026-11-13 |  |  | Check |  |  |  | 2 | 0%
ADM-2.1 | ADM-2 | Admin & Possession | Electrical permit / notification (ESA) for new circuits & pot lights | Not Started | High | 2 - Rough-in | Electrician | 2026-11-09 | 2026-11-13 |  | ADM-1.4 | Yes |  |  |  | 0 | 0% |  | Usually pulled by your licensed electrician
ADM-2.2 | ADM-2 | Admin & Possession | Check with City of Vaughan whether kitchen/bath/laundry plumbing changes need a building permit | Not Started | Medium | 2 - Rough-in | DIY | 2026-11-09 | 2026-11-20 |  |  | Check |  |  |  | 0 | 0%
MOLD-1 |  | Mold Remediation | Mold assessment & quotes | Planned | High | 1 - Remediation | Remediation Co. | 2026-11-04 | 2026-11-06 |  | ADM-1 | No |  |  |  | 3 | 0%
MOLD-1.1 | MOLD-1 | Mold Remediation | Get 2–3 remediation quotes (attic + basement scope) | Not Started | High | 1 - Remediation | DIY | 2026-11-04 | 2026-11-06 |  |  | No |  |  |  | 0 | 0% |  | Can line up site visits before Nov 4 if seller allows
MOLD-1.2 | MOLD-1 | Mold Remediation | Identify moisture source in attic (bath fans venting into attic, ventilation, roof leak) | Not Started | High | 1 - Remediation | Remediation Co. | 2026-11-04 | 2026-11-06 |  |  | No |  |  |  | 0 | 0% |  | Fix the cause or mold returns
MOLD-1.3 | MOLD-1 | Mold Remediation | Identify moisture source in basement (grading, foundation cracks, humidity, sump) | Not Started | High | 1 - Remediation | Remediation Co. | 2026-11-04 | 2026-11-06 |  |  | No |  |  |  | 0 | 0%
MOLD-2 |  | Mold Remediation | Attic mold remediation | Not Started | High | 1 - Remediation | Remediation Co. | 2026-11-09 | 2026-11-13 |  | MOLD-1 | No |  |  |  | 4 | 0%
MOLD-2.1 | MOLD-2 | Mold Remediation | Set up containment & negative air | Not Started | High | 1 - Remediation | Remediation Co. | 2026-11-09 | 2026-11-09 |  |  | No |  |  |  | 0 | 0%
MOLD-2.2 | MOLD-2 | Mold Remediation | Remove contaminated insulation | Not Started | High | 1 - Remediation | Remediation Co. | 2026-11-09 | 2026-11-10 |  |  | No |  |  |  | 0 | 0% |  | Attic will be open — best window for wiring runs
MOLD-2.3 | MOLD-2 | Mold Remediation | HEPA vacuum, treat & seal roof sheathing | Not Started | High | 1 - Remediation | Remediation Co. | 2026-11-10 | 2026-11-12 |  |  | No |  |  |  | 0 | 0%
MOLD-2.4 | MOLD-2 | Mold Remediation | Correct attic ventilation (baffles, vents, bath fans ducted outside) | Not Started | High | 1 - Remediation | Contractor | 2026-11-12 | 2026-11-13 |  | MOLD-1.2 | No |  |  |  | 0 | 0%
MOLD-3 |  | Mold Remediation | Basement mold remediation | Not Started | High | 1 - Remediation | Remediation Co. | 2026-11-09 | 2026-11-13 |  | MOLD-1 | No |  |  |  | 3 | 0%
MOLD-3.1 | MOLD-3 | Mold Remediation | Containment & removal of affected drywall / insulation | Not Started | High | 1 - Remediation | Remediation Co. | 2026-11-09 | 2026-11-11 |  |  | No |  |  |  | 0 | 0%
MOLD-3.2 | MOLD-3 | Mold Remediation | Clean & treat framing / foundation walls | Not Started | High | 1 - Remediation | Remediation Co. | 2026-11-11 | 2026-11-13 |  |  | No |  |  |  | 0 | 0%
MOLD-3.3 | MOLD-3 | Mold Remediation | Fix moisture source (dehumidifier, grading, crack repair) | Not Started | High | 1 - Remediation | Contractor | 2026-11-11 | 2026-11-20 |  | MOLD-1.3 | No |  |  |  | 0 | 0%
MOLD-4 |  | Mold Remediation | Post-remediation clearance testing (attic & basement) | Not Started | High | 1 - Remediation | Remediation Co. | 2026-11-16 | 2026-11-16 |  | MOLD-2, MOLD-3 | No |  |  |  | 0 | 0% |  | Get clearance report before closing up with insulation
ELEC-1 |  | Electrical Rough-in | Electrical plan | Not Started | High | 2 - Rough-in | Electrician | 2026-11-05 | 2026-11-13 |  | ADM-1.4 | Yes |  |  |  | 3 | 0%
ELEC-1.1 | ELEC-1 | Electrical Rough-in | Hire licensed electrician & get quote | Not Started | High | 2 - Rough-in | DIY | 2026-11-05 | 2026-11-10 |  |  | No |  |  |  | 0 | 0%
ELEC-1.2 | ELEC-1 | Electrical Rough-in | Confirm panel capacity for new circuits (kitchen, laundry, lighting) | Not Started | High | 2 - Rough-in | Electrician | 2026-11-09 | 2026-11-13 |  |  | No |  |  |  | 0 | 0% |  | May need panel upgrade
ELEC-1.3 | ELEC-1 | Electrical Rough-in | Mark room-by-room layout (pot lights, switches, outlets, fans) | Not Started | High | 2 - Rough-in | DIY | 2026-11-05 | 2026-11-13 |  | LGT-1 | No |  |  |  | 0 | 0%
ELEC-2 |  | Electrical Rough-in | Attic wiring rough-in (before insulation) | Not Started | High | 2 - Rough-in | Electrician | 2026-11-17 | 2026-11-20 |  | MOLD-4 | Yes |  |  |  | 3 | 0% |  | Ceiling runs for upstairs pot lights & bath fans
ELEC-2.1 | ELEC-2 | Electrical Rough-in | Run upstairs pot light circuits & switch legs | Not Started | High | 2 - Rough-in | Electrician | 2026-11-17 | 2026-11-19 |  |  | Yes |  |  |  | 0 | 0% |  | Use IC-rated, airtight fixtures under insulation
ELEC-2.2 | ELEC-2 | Electrical Rough-in | Wire bathroom exhaust fans (both upstairs baths) | Not Started | High | 2 - Rough-in | Electrician | 2026-11-18 | 2026-11-19 |  |  | Yes |  |  |  | 0 | 0%
ELEC-2.3 | ELEC-2 | Electrical Rough-in | Rough-in inspection | Not Started | High | 2 - Rough-in | Electrician | 2026-11-23 | 2026-11-23 |  | ELEC-2.1, ELEC-2.2 | Yes |  |  |  | 0 | 0% |  | Must pass before insulation covers wiring
ELEC-3 |  | Electrical Rough-in | Basement wiring rough-in (while walls are open) | Not Started | Medium | 2 - Rough-in | Electrician | 2026-11-17 | 2026-11-27 |  | MOLD-4 | Yes |  |  |  | 0 | 0%
NET-1 |  | Networking | Whole-home network wiring | Not Started | High | 2 - Rough-in | Low-Voltage / AV | 2026-11-05 | 2026-11-20 |  |  | No |  |  |  | 6 | 0%
NET-1.1 | NET-1 | Networking | Pick network/rack location (often basement utility room) | Not Started | High | 2 - Rough-in | DIY | 2026-11-05 | 2026-11-10 |  |  | No |  |  |  | 0 | 0%
NET-1.2 | NET-1 | Networking | List Cat6 drops per room (TVs, offices, desks) | Not Started | High | 2 - Rough-in | DIY | 2026-11-05 | 2026-11-10 |  |  | No |  |  |  | 0 | 0%
NET-1.3 | NET-1 | Networking | Plan ceiling Wi-Fi access point locations | Not Started | Medium | 2 - Rough-in | DIY | 2026-11-05 | 2026-11-10 |  |  | No |  |  |  | 0 | 0%
NET-1.4 | NET-1 | Networking | Pull Cat6 through attic to upstairs rooms & APs | Not Started | High | 2 - Rough-in | Low-Voltage / AV | 2026-11-17 | 2026-11-20 |  | MOLD-4 | No |  |  |  | 0 | 0% |  | Do while attic insulation is out
NET-1.5 | NET-1 | Networking | Run conduit / pull strings for future runs | Not Started | Low | 2 - Rough-in | Low-Voltage / AV | 2026-11-17 | 2026-11-20 |  |  | No |  |  |  | 0 | 0%
NET-1.6 | NET-1 | Networking | Terminate, label & test all runs; install patch panel | Not Started | Medium | 6 - Fixtures & Devices | Low-Voltage / AV |  |  |  |  | No |  |  |  | 0 | 0%
CAM-1 |  | Security Cameras | Security camera system | Not Started | High | 2 - Rough-in | Low-Voltage / AV | 2026-11-05 | 2026-11-20 |  |  | No |  |  |  | 4 | 0%
CAM-1.1 | CAM-1 | Security Cameras | Choose camera locations & coverage (doors, driveway, yard) | Not Started | High | 2 - Rough-in | DIY | 2026-11-05 | 2026-11-10 |  |  | No |  |  |  | 0 | 0%
CAM-1.2 | CAM-1 | Security Cameras | Choose system (PoE cameras + NVR) & NVR location | Not Started | Medium | 2 - Rough-in | DIY | 2026-11-05 | 2026-11-13 |  | NET-1.1 | No |  |  |  | 0 | 0%
CAM-1.3 | CAM-1 | Security Cameras | Run PoE cable through attic to soffit/eave locations | Not Started | High | 2 - Rough-in | Low-Voltage / AV | 2026-11-17 | 2026-11-20 |  | MOLD-4 | No |  |  |  | 0 | 0%
CAM-1.4 | CAM-1 | Security Cameras | Mount cameras, connect NVR, set up app & recording | Not Started | Low | 6 - Fixtures & Devices | Low-Voltage / AV |  |  |  |  | No |  |  |  | 0 | 0%
INS-1 |  | Insulation | Attic insulation | Not Started | High | 3 - Insulation & Drywall | Insulation Co. | 2026-11-24 | 2026-11-26 |  | ELEC-2.3, NET-1.4, CAM-1.3 | No |  |  |  | 4 | 0% |  | Only after all attic wiring is done & inspected
INS-1.1 | INS-1 | Insulation | Air-seal top plates & ceiling penetrations | Not Started | High | 3 - Insulation & Drywall | Insulation Co. | 2026-11-24 | 2026-11-24 |  |  | No |  |  |  | 0 | 0%
INS-1.2 | INS-1 | Insulation | Install baffles at eaves | Not Started | High | 3 - Insulation & Drywall | Insulation Co. | 2026-11-24 | 2026-11-24 |  |  | No |  |  |  | 0 | 0%
INS-1.3 | INS-1 | Insulation | Blow in insulation to target R-value | Not Started | High | 3 - Insulation & Drywall | Insulation Co. | 2026-11-25 | 2026-11-26 |  |  | No |  |  |  | 0 | 0% |  | Confirm R-value with installer
INS-1.4 | INS-1 | Insulation | Check energy rebate eligibility before work starts | Not Started | Medium | 3 - Insulation & Drywall | DIY | 2026-11-05 | 2026-11-13 |  |  | No |  |  |  | 0 | 0% |  | Some programs require a pre-work assessment
INS-2 |  | Insulation | Basement wall insulation | Not Started | Medium | 3 - Insulation & Drywall | Insulation Co. | 2026-11-30 | 2026-12-04 |  | ELEC-3, MOLD-3.3 | No |  |  |  | 0 | 0%
LGT-1 |  | Lighting & Pot Lights | Lighting layout & selection | Not Started | High | 2 - Rough-in | DIY | 2026-11-05 | 2026-11-13 |  |  | No |  |  |  | 3 | 0%
LGT-1.1 | LGT-1 | Lighting & Pot Lights | Pot light count & spacing per room | Not Started | High | 2 - Rough-in | DIY | 2026-11-05 | 2026-11-13 |  |  | No |  |  |  | 0 | 0%
LGT-1.2 | LGT-1 | Lighting & Pot Lights | Choose colour temperature / dimmable LED wafer lights | Not Started | Medium | 2 - Rough-in | DIY |  |  |  |  | No |  |  |  | 0 | 0%
LGT-1.3 | LGT-1 | Lighting & Pot Lights | Choose dimmers / smart switches | Not Started | Low | 6 - Fixtures & Devices | DIY |  |  |  |  | No |  |  |  | 0 | 0%
LGT-2 |  | Lighting & Pot Lights | Main floor pot lights | Not Started | Medium | 2 - Rough-in | Electrician |  |  |  | ELEC-1 | Yes |  |  |  | 0 | 0%
LGT-3 |  | Lighting & Pot Lights | Install fixtures & trims after paint | Not Started | Low | 6 - Fixtures & Devices | Electrician |  |  |  | TRIM-5 | Yes |  |  |  | 0 | 0%
KIT-1 |  | Kitchen | Design: layout, cabinets, counters, appliances | Not Started | Medium | 4 - Finishes | DIY |  |  |  |  | No |  |  |  | 3 | 0%
KIT-1.1 | KIT-1 | Kitchen | Measure room & sketch layout | Not Started | Medium | 4 - Finishes | DIY |  |  |  |  | No |  |  |  | 0 | 0%
KIT-1.2 | KIT-1 | Kitchen | Get cabinet & countertop quotes | Not Started | Medium | 4 - Finishes | DIY |  |  |  |  | No |  |  |  | 0 | 0%
KIT-1.3 | KIT-1 | Kitchen | Pick appliances (confirm sizes before cabinets) | Not Started | Medium | 4 - Finishes | DIY |  |  |  |  | No |  |  |  | 0 | 0%
KIT-2 |  | Kitchen | Demolition | Not Started | Medium | 2 - Rough-in | Contractor |  |  |  | KIT-1 | No |  |  |  | 0 | 0%
KIT-3 |  | Kitchen | Plumbing rough-in (sink, dishwasher, fridge line) | Not Started | Medium | 2 - Rough-in | Plumber |  |  |  | KIT-2 | Check |  |  |  | 0 | 0%
KIT-4 |  | Kitchen | Electrical rough-in (dedicated circuits, under-cabinet lights) | Not Started | Medium | 2 - Rough-in | Electrician |  |  |  | KIT-2 | Yes |  |  |  | 0 | 0%
KIT-5 |  | Kitchen | Drywall & paint | Not Started | Medium | 3 - Insulation & Drywall | Contractor |  |  |  | KIT-3, KIT-4 | No |  |  |  | 0 | 0%
KIT-6 |  | Kitchen | Flooring | Not Started | Medium | 4 - Finishes | Contractor |  |  |  | KIT-5 | No |  |  |  | 0 | 0%
KIT-7 |  | Kitchen | Cabinet install | Not Started | Medium | 4 - Finishes | Contractor |  |  |  | KIT-6 | No |  |  |  | 0 | 0%
KIT-8 |  | Kitchen | Countertop template & install | Not Started | Medium | 4 - Finishes | Contractor |  |  |  | KIT-7 | No |  |  |  | 0 | 0%
KIT-9 |  | Kitchen | Backsplash | Not Started | Medium | 4 - Finishes | Contractor |  |  |  | KIT-8 | No |  |  |  | 0 | 0%
KIT-10 |  | Kitchen | Appliances & plumbing fixtures | Not Started | Medium | 6 - Fixtures & Devices | Plumber |  |  |  | KIT-8 | No |  |  |  | 0 | 0%
LAU-1 |  | Laundry Room | Design: layout, cabinets / shelving, sink | Not Started | Medium | 4 - Finishes | DIY |  |  |  |  | No |  |  |  | 0 | 0%
LAU-2 |  | Laundry Room | Plumbing: supply, drain, washer box, floor drain check | Not Started | Medium | 2 - Rough-in | Plumber |  |  |  | LAU-1 | Check |  |  |  | 0 | 0%
LAU-3 |  | Laundry Room | Electrical: 240V dryer & washer circuits | Not Started | Medium | 2 - Rough-in | Electrician |  |  |  | LAU-1 | Yes |  |  |  | 0 | 0%
LAU-4 |  | Laundry Room | Dryer vent run to exterior | Not Started | Medium | 2 - Rough-in | Contractor |  |  |  | LAU-1 | No |  |  |  | 0 | 0%
LAU-5 |  | Laundry Room | Flooring | Not Started | Medium | 4 - Finishes | Contractor |  |  |  | LAU-2, LAU-3 | No |  |  |  | 0 | 0%
LAU-6 |  | Laundry Room | Cabinets, counter & shelving | Not Started | Medium | 4 - Finishes | Contractor |  |  |  | LAU-5 | No |  |  |  | 0 | 0%
LAU-7 |  | Laundry Room | Install washer & dryer | Not Started | Medium | 6 - Fixtures & Devices | DIY |  |  |  | LAU-6 | No |  |  |  | 0 | 0%
BA1-1 |  | Upstairs Bath 1 | Design: vanity, tile, shower/tub, fixtures | Not Started | Medium | 4 - Finishes | DIY |  |  |  |  | No |  |  |  | 0 | 0%
BA1-2 |  | Upstairs Bath 1 | Demolition | Not Started | Medium | 2 - Rough-in | Contractor |  |  |  | BA1-1 | No |  |  |  | 0 | 0%
BA1-3 |  | Upstairs Bath 1 | Plumbing rough-in | Not Started | Medium | 2 - Rough-in | Plumber |  |  |  | BA1-2 | Check |  |  |  | 0 | 0%
BA1-4 |  | Upstairs Bath 1 | Exhaust fan ducted to exterior | Not Started | Medium | 2 - Rough-in | Electrician |  |  |  | BA1-2 | Yes |  |  |  | 0 | 0%
BA1-5 |  | Upstairs Bath 1 | Shower waterproofing & cement board | Not Started | Medium | 3 - Insulation & Drywall | Contractor |  |  |  | BA1-3 | No |  |  |  | 0 | 0%
BA1-6 |  | Upstairs Bath 1 | Tile: floor & shower walls | Not Started | Medium | 4 - Finishes | Contractor |  |  |  | BA1-5 | No |  |  |  | 0 | 0%
BA1-7 |  | Upstairs Bath 1 | Vanity, toilet & fixtures | Not Started | Medium | 6 - Fixtures & Devices | Plumber |  |  |  | BA1-6 | No |  |  |  | 0 | 0%
BA1-8 |  | Upstairs Bath 1 | Mirror, lighting & accessories | Not Started | Medium | 6 - Fixtures & Devices | DIY |  |  |  | BA1-7 | No |  |  |  | 0 | 0%
BA2-1 |  | Upstairs Bath 2 | Design: vanity, tile, shower/tub, fixtures | Not Started | Medium | 4 - Finishes | DIY |  |  |  |  | No |  |  |  | 0 | 0%
BA2-2 |  | Upstairs Bath 2 | Demolition | Not Started | Medium | 2 - Rough-in | Contractor |  |  |  | BA2-1 | No |  |  |  | 0 | 0%
BA2-3 |  | Upstairs Bath 2 | Plumbing rough-in | Not Started | Medium | 2 - Rough-in | Plumber |  |  |  | BA2-2 | Check |  |  |  | 0 | 0%
BA2-4 |  | Upstairs Bath 2 | Exhaust fan ducted to exterior | Not Started | Medium | 2 - Rough-in | Electrician |  |  |  | BA2-2 | Yes |  |  |  | 0 | 0%
BA2-5 |  | Upstairs Bath 2 | Shower waterproofing & cement board | Not Started | Medium | 3 - Insulation & Drywall | Contractor |  |  |  | BA2-3 | No |  |  |  | 0 | 0%
BA2-6 |  | Upstairs Bath 2 | Tile: floor & shower walls | Not Started | Medium | 4 - Finishes | Contractor |  |  |  | BA2-5 | No |  |  |  | 0 | 0%
BA2-7 |  | Upstairs Bath 2 | Vanity, toilet & fixtures | Not Started | Medium | 6 - Fixtures & Devices | Plumber |  |  |  | BA2-6 | No |  |  |  | 0 | 0%
BA2-8 |  | Upstairs Bath 2 | Mirror, lighting & accessories | Not Started | Medium | 6 - Fixtures & Devices | DIY |  |  |  | BA2-7 | No |  |  |  | 0 | 0%
TRIM-1 |  | Trim & Doors (Whole House) | Measure baseboard & casing linear feet room by room | Not Started | Low | 5 - Trim & Paint | DIY |  |  |  |  | No |  |  |  | 0 | 0%
TRIM-2 |  | Trim & Doors (Whole House) | Choose baseboard, casing & door styles | Not Started | Low | 5 - Trim & Paint | DIY |  |  |  |  | No |  |  |  | 0 | 0%
TRIM-3 |  | Trim & Doors (Whole House) | Order interior doors & trim (allow lead time) | Not Started | Low | 5 - Trim & Paint | DIY |  |  |  | TRIM-2 | No |  |  |  | 0 | 0%
TRIM-4 |  | Trim & Doors (Whole House) | Remove old trim & doors | Not Started | Low | 5 - Trim & Paint | Contractor |  |  |  | TRIM-3 | No |  |  |  | 0 | 0%
TRIM-5 |  | Trim & Doors (Whole House) | Install doors, casings & baseboards | Not Started | Low | 5 - Trim & Paint | Contractor |  |  |  | TRIM-4 | No |  |  |  | 0 | 0% |  | Do after flooring & wall paint in each area
TRIM-6 |  | Trim & Doors (Whole House) | Fill, caulk & paint trim | Not Started | Low | 5 - Trim & Paint | DIY |  |  |  | TRIM-5 | No |  |  |  | 0 | 0%
Formulas:
Flag = IF(OR([ID]="",[Status]="Done",[Due]=""),"",IF([Due]<TODAY(),"OVERDUE",IF([Due]-TODAY()<=7,"Due this week","")))
Note on N4: Enter costs on sub-tasks, or on a task that has no sub-tasks. Dashboard totals only count rows with 0 sub-tasks, so parent rows aren't double-counted.

## Contacts & Quotes
Contractors, Contacts & Quotes
Row 4 is an example — overwrite or delete it.
Name | Company | Trade | Phone | Email | Area(s) | Quote ($) | Quote Date | Hired? | Start Date | Notes
Jane Smith | ABC Mold Solutions | Remediation Co. | (905) 555-0100 | jane@example.com | Attic, Basement | 6500 | 2026-10-28 | No |  | Example row — includes air testing

## Lists
Areas | Status | Priority | Phase | Assigned To | Permit? | Add new options at the bottom of any column (dropdowns read down to row 40).
Admin & Possession | Not Started | High | 1 - Remediation | DIY | Yes
Mold Remediation | Planned | Medium | 2 - Rough-in | Contractor | No
Electrical Rough-in | In Progress | Low | 3 - Insulation & Drywall | Electrician | Check
Networking | Waiting (Trade/Materials) |  | 4 - Finishes | Plumber
Security Cameras | On Hold |  | 5 - Trim & Paint | Remediation Co.
Insulation | Done |  | 6 - Fixtures & Devices | Insulation Co.
Lighting & Pot Lights |  |  |  | Low-Voltage / AV
Kitchen |  |  |  | TBD
Laundry Room
Upstairs Bath 1
Upstairs Bath 2
Trim & Doors (Whole House)
Other